## Fix Tracker
WAH4H — Post-UAT Fix Tracker ¦ v2.0 Complete
Module | TC ID | Priority | Area / Sub-Issue | Issue Description | Status | Changed By | Date Changed | Comments / Feedback
Authentication | TC-AUTH-002 | High | Registration — OTP Disabled | OTP is disabled during testing so registration completes without OTP verification; production behavior unconfirmed | Not Started
Authentication | TC-AUTH-002 | High | Registration — No Email Confirmation | No confirmation email sent on successful registration | Not Started
Authentication | TC-AUTH-002 | High | Registration — Password Policy | Password position/uppercase requirement is missing or not enforced | Not Started
Authentication | TC-AUTH-003 | High | Duplicate Email Feedback | No real-time inline error when entering an already-registered email; error only fires on submit | Not Started
Authentication | TC-AUTH-003 | High | Registration Rate Limit | False 'Too many attempts' error fires when navigating back and forth between registration pages | Not Started
Authentication | TC-AUTH-005 | Critical | OTP — Not Delivered | OTP email not received by testers; no fallback or resend option shown | Not Started
Authentication | TC-AUTH-005 | Critical | OTP — No Resend Button | After OTP failure there is no Resend OTP button on the verification screen | Not Started
Authentication | TC-AUTH-005 | Critical | OTP — System Failure on Submit | System failure reported on OTP submission; endpoint returns no proper response | Not Started
Authentication | TC-AUTH-005 | High | Post-Reset Sidebar Missing | After password reset, user lands on dashboard with no visible sidebar navigation tabs | Not Started
Authentication | TC-AUTH-007 | High | Session Timeout — Move Mouse Not Working | 'Move your mouse' stay-alive interaction does not reset the idle timer | Not Started
Authentication | TC-AUTH-007 | High | Session Timeout — Threshold Too Short | Idle timeout fires too quickly; testers flag it as disruptive to normal clinical workflows | Not Started
Authentication | TC-AUTH-007 | Medium | Wrong Legal Reference in Warning | Warning message references HIPAA — must be changed to RA 10173; HIPAA is US law, not applicable in PH | Not Started
Authentication | TC-AUTH-008 | High | Sidebar RBAC Mismatch | Non-admin roles can see modules they should not have access to; sidebar visibility rules not matching RBAC matrix | Not Started
Patients | TC-PAT-001 | High | Mandatory Fields Not Enforced | Some fields that must be required are not enforced as mandatory on patient registration form | Not Started
Patients | TC-PAT-002 | High | No Per-Field Validation Messages | Validation errors are generic; system does not specify which field failed or why | Not Started
Patients | TC-PAT-002 | High | No Visual Field Error Indicator | No highlighting or focus on the field that caused the error; user cannot see which field is the problem | Not Started
Patients | TC-PAT-002 | High | PWD Status Unverified | PWD (Person with Disability) status can be checked without any verification or documentation requirement | Not Started
Patients | TC-PAT-002 | Medium | Country Field Re-triggers Processing | After filling all fields, changing the Country field forces the form to re-process unnecessarily | Not Started
Patients | TC-PAT-002 | Medium | Suffix Field — No Enum | Suffix is free-text; should use a validated enum (Jr., Sr., II, III, etc.) | Not Started
Patients | TC-PAT-002 | Medium | Premature Validation on Pro Quals | Error indicators appear on Professional Qualifications fields before user has typed anything | Not Started
Patients | TC-PAT-003 | Critical | Search by Name Not Working | Searching by patient name returns no results; search function non-functional | Not Started
Patients | TC-PAT-003 | Critical | Patient Record Not Loading on Click | Clicking a search result does not open the patient record inline | Not Started
Patients | TC-PAT-003 | Critical | Insurance ID False-Positive Duplicate Error | 'Error: insurance ID is already registered' fires incorrectly on new patient registrations; likely stale form state | Not Started
Patients | TC-PAT-003 | Medium | Suffix Not Accounted for in Search | Search does not handle suffix variations (e.g., 'Juan dela Cruz Jr.' vs 'Juan dela Cruz') | Not Started
Patients | TC-PAT-004 | High | Fields Drop Out on Edit Click | Some fields disappear from the form when the Edit button is clicked | Not Started
Patients | TC-PAT-004 | High | Data Lost on Section Navigation | Data entered in one form section is lost when navigating to another section before saving | Not Started
Patients | TC-PAT-004 | Medium | Indigenous Status Checkbox — Fields Not Clearing | When Indigenous Status is unchecked, related dependent fields do not clear | Not Started
Patients | TC-PAT-004 | Medium | Address Fields Missing in Edit Mode | Address Information fields specifically go missing when switching to Edit mode | Not Started
Patients | TC-PAT-005 | High | Future/Invalid Dates Accepted on Conditions | Onset date field on conditions accepts future dates and implausibly backdated dates without validation | Not Started
Patients | TC-PAT-005 | Medium | Condition Identifier Editable | FHIR Identifier field on Condition is user-editable; must be system-generated and read-only per FHIR R4 | Not Started
Patients | TC-PAT-006 | Critical | Allergy Data Not Persisted | Allergy record is created but data is not saved to the database; disappears on page reload | Not Started
Patients | TC-PAT-006 | Critical | Allergy Save — No Feedback on Failure | No error message shown when allergy save fails; user sees apparent success but data is lost | Not Started
Patients | TC-PAT-006 | High | No Criticality Visual Indicator | No visual flag or highlight shown when an allergy has a high-criticality rating; dangerous allergies must be prominently marked | Not Started
Patients | TC-PAT-006 | Medium | Allergy FHIR Identifier Editable | FHIR Identifier field on Allergy record is editable; must be system-generated and read-only | Not Started
Patients | TC-PAT-006 | Medium | Date Picker Does Not Close Properly | Date picker on allergy form does not close after selection | Not Started
Patients | TC-PAT-007 | Critical | Allergy Fetch — HTTP 400 | HTTP 400 error on fetching allergy records; allergy list fails to load | Not Started
Patients | TC-PAT-007 | Critical | Previously Saved Allergy Not Visible on Re-open | Saved allergy records do not appear when the Allergies tab is reopened | Not Started
Patients | TC-PAT-007 | High | Edit Allergy — Old Data Not Reflected | When editing a previously saved allergy, the form does not pre-fill with the existing data | Not Started
Patients | TC-PAT-008 | Critical | Immunization Data Not Persisted | Immunization record created but data not saved to database; HTTP 400 on save | Not Started
Patients | TC-PAT-008 | Critical | Missing Required Fields on Immunization Form | Required fields for immunization creation are absent from the form | Not Started
Patients | TC-PAT-008 | High | Immunization Status Defaults to Completed | Status defaults to 'Completed'; should default to 'Scheduled' or be user-selectable | Not Started
Patients | TC-PAT-008 | High | No Field-Level Error Focus | On validation failure, page does not scroll to or highlight the problematic field | Not Started
Patients | TC-PAT-008 | Medium | Immunization FHIR Identifier Editable | FHIR Identifier field on Immunization record is editable; must be system-generated read-only | Not Started
Patients | TC-PAT-009 | High | WAH4P Integration — Untestable (No Test Data) | TC-PAT-009 (push/pull patient to external provider) could not be tested because WAH4P/WAH4PC clinic test data was never provided to testers; blocked by missing prerequisite, not a code issue | Not Started
Admission | TC-ADM-001 | High | No Inline New Patient Shortcut | No 'Register New Patient' button within the encounter creation flow; user must exit and register separately | Not Started
Admission | TC-ADM-001 | High | Future Admission Date Not Blocked | Admission date field accepts future dates; must be restricted to today or earlier | Not Started
Admission | TC-ADM-001 | High | Attending Physician Dropdown Format | Dropdown shows full concatenated string (e.g., 'Aries Canlas Physician'); should show 'Name, Specialty' only | Not Started
Admission | TC-ADM-001 | Medium | Diagnosis Has Billing and Discharge Options on New Admission | Billing and discharge options appear on new admission diagnosis field; inappropriate at this stage | Not Started
Admission | TC-ADM-001 | Medium | Diet Preferences — No Mutual Exclusivity | All diet preference checkboxes can be selected simultaneously; needs logical constraints | Not Started
Admission | TC-ADM-001 | Medium | No Printable Admission Summary | No printable summary at end of admission form showing encoder name, timestamp, and entered data | Not Started
Admission | TC-ADM-004 | High | End Encounter Not Discoverable | Multiple testers could not find the 'End Encounter' action in the UI; must be surfaced clearly | Not Started
Admission | TC-ADM-004 | High | Terminology Inconsistency — Admission vs Encounter | UI uses 'Admission'; UAT docs use 'Encounter'; must be standardized across UI, docs, and labels | Not Started
Admission | TC-ADM-001 | Medium | Record-Level RBAC Not Enforced | Doctors can view patient records not assigned to them; RBAC enforced at sidebar level only, not at data/query level | Not Started
Admission | TC-ADM-003 | Medium | No Restriction on Backdated Record Date | Record date can be set 24+ years in the past; no reasonable minimum date restriction | Not Started
Appointments | TC-APT-001 | High | Full Module Untested — Create Appointment | TC-APT-001 has no tester responses recorded; must be executed in next UAT cycle | Not Started
Appointments | TC-APT-002 | High | Full Module Untested — Cancel Appointment | TC-APT-002 has no tester responses recorded; must be executed in next UAT cycle | Not Started
Appointments | TC-APT-003 | High | Full Module Untested — Mark Patient Arrived | TC-APT-003 has no tester responses recorded; must be executed in next UAT cycle | Not Started
Appointments | TC-APT-003 | High | Arrived Status — No Date Gate | Patient can be marked as Arrived regardless of whether the appointment date matches today | Not Started
Appointments | TC-APT-004 | High | Full Module Untested — Practitioner Schedule | TC-APT-004 has no tester responses recorded; must be executed in next UAT cycle | Not Started
Appointments | TC-APT-004 | Medium | Schedule Creation Should Be Admin/HR Function | Each doctor should not self-manage their own schedule; should be managed by admin or HR role | Not Started
Appointments | TC-APT-004 | Medium | Service Type Field Unnecessary | Service Type field on appointment creation is flagged as unnecessary; should be removed or made optional | Not Started
Appointments | TC-APT-004 | Medium | Raw API Errors Exposed to Users | Raw JSON error (e.g., {"identifier": ["This field is required."]}) is shown directly to users; must be caught and translated | Not Started
Monitoring | TC-MON-001 | Critical | Date and Time Field Missing from Vital Signs Form | Date/time field is absent from the vital signs entry form; observations cannot be timestamped | Not Started
Monitoring | TC-MON-001 | Critical | Observation Type, Value, and Units Fields Missing | Core fields for recording a vital sign observation are not present on the form | Not Started
Monitoring | TC-MON-001 | High | No Deduplication Check | Identical vital sign entries can be submitted multiple times with no warning or duplicate detection | Not Started
Monitoring | TC-MON-001 | High | O2 Saturation Accepts Out-of-Range Values | O2 saturation field accepts values outside 0–100%; must be restricted to physiologically valid range | Not Started
Monitoring | TC-MON-001 | Medium | Observation Terminology Unclear | 'Observation' label confuses testers expecting 'Vital Signs'; terminology should align with clinical expectation | Not Started
Monitoring | TC-MON-003 | High | No Input Restrictions on Vital Sign Fields | Vital sign fields accept any numeric value including negatives and physiologically impossible numbers | Not Started
Monitoring | TC-MON-003 | High | Negative Values Accepted | Negative values can be entered for all vital sign fields; must be blocked | Not Started
Monitoring | TC-MON-003 | High | Abnormal Observation State Not Displayed | After saving an out-of-range observation, the flagged/abnormal state is not visually shown in the timeline | Not Started
Monitoring | TC-MON-003 | Medium | Observation Filter Missing or Incomplete | Filtering observations by type returns unclear or incomplete results | Not Started
Monitoring | TC-MON-005 | High | Monitoring to Billing Charge Item Link Not Implemented | No way to create a charge item from within Monitoring; linkage to billing is entirely missing | Not Started
Laboratory | TC-LAB-001 | Critical | Page Crashes on Lab Request Submit | ERROR UPON LOADING PAGE on submit; token is blacklisted error — JWT issue causing page crash | Not Started
Laboratory | TC-LAB-001 | Critical | Lab Request List Fails to Load | Lab request list page fails to load on open; likely same JWT/token issue | Not Started
Laboratory | TC-LAB-001 | High | Lab Request Placed in Wrong Tab | Lab request appears inside the Monitoring tab, not Laboratory tab; incorrect module placement causing tester confusion | Not Started
Laboratory | TC-LAB-001 | Medium | Lab Request Lacks Verification Step | No confirmation or verification step before lab request is submitted | Not Started
Laboratory | TC-LAB-003 | Critical | Specimen Recording Feature Not Found | Specimen recording function not accessible; multiple testers could not locate it | Not Started
Laboratory | TC-LAB-003 | Critical | Result Entry Accepts Blank Submissions | Lab result entry form submits successfully with all fields blank; no required field validation | Not Started
Laboratory | TC-LAB-003 | High | No Input Restrictions on Result Values | No restrictions, limitations, or range validations on result value fields | Not Started
Laboratory | TC-LAB-003 | High | Lab Result Status Page Fails to Load | Status page for an in-progress lab report fails to load | Not Started
Laboratory | TC-LAB-005 | High | Result Release Feature Missing | Release results to attending physician function does not exist; entirely unimplemented | Not Started
Pharmacy | TC-PHR-001 | High | Dispense Not Accessible from Pharmacy Tab | Dispense medication function is not navigable from within the Pharmacy tab; found in a different location | Not Started
Pharmacy | TC-PHR-001 | High | No Allergy Warning on Prescription | When prescribing, no warning is shown if the medication conflicts with a patient's recorded allergy | Not Started
Pharmacy | TC-PHR-001 | High | No Dose/Frequency Restrictions | Dose and frequency fields have no input limits or validation; any value accepted | Not Started
Pharmacy | TC-PHR-003 | High | Stock Status After Dispense Unclear | After a prescription is dispensed, stock status (remaining, reserved) is not clearly shown | Not Started
Pharmacy | TC-PHR-003 | High | Prescription-to-Dispense Flow Failing | Stock deduction fails during the prescribe-to-dispense flow; prescription cannot be completed | Not Started
Pharmacy | TC-PHR-003 | Medium | No Input Restrictions on Dispense Fields | Required fields on dispense form are unclear or absent; missing validation | Not Started
Pharmacy | TC-PHR-003 | Medium | STAT Priority Not Visually Distinct Enough | STAT prescriptions appear at top of queue but need stronger visual differentiation from routine orders | Not Started
Discharge | TC-DIS-001 | Critical | Encounter and Conditions Not Listed in Discharge Form | When a patient is selected in discharge, their encounter and active conditions are not populated in the form | Not Started
Discharge | TC-DIS-001 | Critical | Datetime Field Cannot Be Set | Discharge datetime field cannot be interacted with or set by the user | Not Started
Discharge | TC-DIS-001 | Critical | ICD-10 Dropdown Missing Free-Text Fallback | ICD-10 discharge diagnosis dropdown does not cover all codes; no free-text fallback for codes not in list | Not Started
Discharge | TC-DIS-001 | High | No Pre-Save Review Screen | No comprehensive summary shown before final submission; testers flagged this as a data integrity risk | Not Started
Discharge | TC-DIS-001 | High | Remove Button Is Ambiguous | Generic 'Remove' button on discharge queue is medically ambiguous; replace with: Discharge, Transfer, Cancel Admission, Archive | Not Started
Discharge | TC-DIS-001 | High | Discharge Documents Not Immediately Printable | Documents must be immediately printable on finalization; currently requires manual file search and download | Not Started
Discharge | TC-DIS-001 | Medium | Redundant Data in Review and Update Popup | 'Review and Update' popup shows same content already visible in the right panel; UX is redundant and confusing | Not Started
Discharge | TC-DIS-002 | Critical | No Draft State for Discharge | Discharge form has no draft save; TC-DIS-003 and TC-DIS-004 are directly blocked by this | Not Started
Discharge | TC-DIS-003 | Critical | Finalize Discharge Blocked by No Draft | TC-DIS-003 cannot be tested until TC-DIS-002 draft save is implemented; status change to Finalized not working | Not Started
Discharge | TC-DIS-004 | High | Discharge Summary View Does Not Exist | View discharge summary feature is entirely missing; confirmed absent on localhost | Not Started
Billing | TC-BIL-001 | High | Patient and Encounter Not Preloaded from Context | Navigating to Billing from an encounter does not carry over patient/encounter context; requires manual re-selection | Not Started
Billing | TC-BIL-001 | High | Invoice Date Not Auto-Filled | Invoice creation date is not auto-populated with the current date; must be manually entered | Not Started
Billing | TC-BIL-001 | High | Encounters Not Listed When Selecting Patient | When selecting a patient in billing, their encounters are not listed for selection | Not Started
Billing | TC-BIL-001 | Medium | Charge Item Rates Not Pre-Configured | Item rates should be pre-set by an authorized role (Financial Officer) and auto-loaded; currently all manual | Not Started
Billing | TC-BIL-002 | High | Invoice Creation Skips to Process Payment | Saving invoice jumps directly to Process Payment step; invoice draft step is bypassed | Not Started
Billing | TC-BIL-002 | High | No Draft Save for Invoice | Invoice cannot be saved as draft; must be set as Issued immediately with no intermediate state | Not Started
Billing | TC-BIL-002 | Medium | Missing Fields in Invoice Form | Some required fields are missing from the invoice creation form | Not Started
Billing | TC-BIL-003 | Critical | Record Payment Module Entirely Missing | No payment recording function or module exists anywhere in the system | Not Started
Billing | TC-BIL-003 | Critical | System Reports Payment Success Falsely | System states payment was successful even though no payment module exists; misleading confirmation | Not Started
Billing | TC-BIL-003 | High | Redirection Logic Error After Invoice | After invoice flow, system redirects incorrectly | Not Started
Billing | TC-BIL-004 | Critical | Payment Reconciliation Module Entirely Missing | Reconciliation section does not exist; cannot link payments to claim line items or flag discrepancies | Not Started
eClaims | TC-PHL-001 | Critical | PhilHealth ID Cannot Be Decoded | System cannot read encoded PhilHealth IDs from patient records; root cause is encoding/decoding mismatch; blocks all eClaims | Not Started
eClaims | TC-PHL-001 | Critical | Raw API Error Exposed on insurer_id Field | Raw JSON error for insurer_id field is shown directly to the user with no friendly message | Not Started
eClaims | TC-PHL-001 | High | No Restrictions on eClaims Data Entry Fields | eClaims form fields have no validation or restrictions; any value accepted | Not Started
eClaims | TC-PHL-003 | Critical | PhilHealth Integration Endpoint Not Functional | PhilHealth integration endpoint is non-functional; no data exchange possible | Not Started
eClaims | TC-PHL-003 | Medium | No Auto-Trigger for Eligible Admissions | Suggestion: when a PhilHealth-eligible patient is admitted and procedure is covered, system should prompt to prepare an eClaims document | Not Started
Dashboard | TC-DASH-001 | Low | KPI Data May Not Reflect Accurate State | Dashboard KPI widgets show no data for roles with no linked records; verify data feeds once other modules are fixed | Not Started
Dashboard | TC-DASH-002 | Low | No Failures Recorded | No failures recorded for TC-DASH-002; verify completeness once dependent modules (Lab, Pharmacy, Billing) are fixed | Not Started
Admin Panel | TC-ADMPANEL-001 | Critical | Admin Credentials Not Working | Admin test accounts had invalid credentials during UAT; admin login blocked for some testers | Not Started
Admin Panel | TC-ADMPANEL-001 | Critical | Page Refresh Logs Admin Out | Refreshing the page in the Admin module ends the session and redirects to login | Not Started
Admin Panel | TC-ADMPANEL-001 | High | Facility List Not Auto-Loaded from NHFR | Facility list in organization settings is not populated from NHFR; must be auto-loaded based on NHFR registration | Not Started
Admin Panel | TC-ADMPANEL-001 | Medium | No Hospital Logo Upload | Organization Settings has no logo upload; logo is needed for printed documents (letterheads, discharge summaries) | Not Started
Admin Panel | TC-ADMPANEL-001 | Medium | No Change Summary Before Save | Saving organization settings applies changes immediately with no confirmation summary of what was changed | Not Started
Admin Panel | TC-ADMPANEL-002 | High | No Reset Password Function | Admin cannot reset a user's password; no such button or flow exists in User Management | Not Started
Admin Panel | TC-ADMPANEL-002 | High | No Pagination or Search in User List | User Management list has no pagination or search; unusable at scale | Not Started
Admin Panel | TC-ADMPANEL-002 | High | No Single-Session Enforcement | Multiple concurrent sessions allowed per account; should enforce one active session per account | Not Started
Admin Panel | TC-ADMPANEL-002 | Medium | No Verification Step Before Role Change | Changing a user's role is applied immediately with no confirmation or verification step | Not Started
Admin Panel | TC-ADMPANEL-003 | Critical | Role-Module Config Save Not Persisted | Saving role-module access changes does not persist via API; changes are lost on page reload | Not Started
Admin Panel | TC-ADMPANEL-003 | Critical | Module Assignment Not Reflected After Save | After saving, the role-module access matrix does not reflect the saved state | Not Started
Admin Panel | TC-ADMPANEL-003 | High | Doctors Can Access Admin Module | Role-module matrix allows Doctor role to access the Admin module; must be locked out | Not Started
Admin Panel | TC-ADMPANEL-003 | High | No Lock on Required Modules Per Role | Admin can accidentally remove required module access from a role (e.g., remove Patients from Doctor) | Not Started
Admin Panel | TC-ADMPANEL-003 | Medium | No Confirmation Step Before Applying Role Changes | Role-module changes are applied without a verification or summary confirmation step | Not Started
Account Settings | TC-SET-001 | Critical | OTP Failure Blocks All Profile Changes | All account setting changes requiring OTP (password change, email) are blocked because OTP is non-functional | Not Started
Account Settings | TC-SET-001 | High | Display Name Cannot Be Updated | Display name field change does not save; fails silently | Not Started
Account Settings | TC-SET-001 | High | Some Profile Fields Cannot Be Edited | Certain profile fields are not responding to edit; changes cannot be saved | Not Started
Account Settings | TC-SET-001 | Medium | Read-Only Fields Should Be Disabled | Fields that should not be user-editable (role, system ID) should be visually disabled/locked, not just unresponsive | Not Started
Security | TC-SEC-001 | High | Unauthenticated API Rejection — Not Tested | TC-SEC-001 not tested; staging not configured to run backend security tests | Not Started
Security | TC-SEC-002 | High | JWT Expiry and Role Enforcement — Not Tested | TC-SEC-002 not tested; expired tokens and cross-role access rejection not verified | Not Started
Security | TC-SEC-003 | High | Rate Limiting on Login Endpoint — Not Tested | TC-SEC-003 not tested; rate limiting on login endpoint not verified | Not Started
Security | TC-SEC-004 | High | Rate Limiting on Password Reset — Not Tested | TC-SEC-004 not tested; rate limiting on password reset endpoint not verified | Not Started
Security | TC-SEC-005 | High | Webhook Authentication — Not Tested | TC-SEC-005 not tested; webhook endpoint auth not verified | Not Started
Cross-Cutting | — | Critical | OTP System Non-Functional System-Wide | OTP email delivery is broken across all modules; must be fixed before any OTP-dependent flow can be re-tested | Not Started
Cross-Cutting | — | Critical | Raw API Errors Exposed to End Users | Raw JSON API error responses are displayed to end users across multiple modules; all must be caught and translated to friendly messages | Not Started
Cross-Cutting | — | Critical | PhilHealth ID Encoding/Decoding Broken | Encoded PhilHealth IDs cannot be decoded by the system; blocks Patients display, Billing, and all eClaims | Not Started
Cross-Cutting | — | High | Page Refresh Logs Users Out | Refreshing the page ends the session in Admin and possibly other modules; JWT refresh token or cookie handling is broken | Not Started
Cross-Cutting | — | High | Patient/Encounter Context Not Carried Over | Patient and encounter context is not automatically passed from Admission to Discharge to Billing; requires manual re-selection at each step | Not Started
Cross-Cutting | — | High | Date/Time Validation Missing Across Modules | Future dates, past dates beyond reason, and invalid datetimes accepted across Patients, Admission, Monitoring, Discharge, Appointments | Not Started
Cross-Cutting | — | High | Record-Level RBAC Not Enforced | Module-level sidebar RBAC exists but queries are not filtered by record ownership/assignment; users see records they should not | Not Started
Cross-Cutting | — | High | Terminology Inconsistency — Admission vs Encounter | 'Admission' (UI) and 'Encounter' (FHIR/UAT docs) used interchangeably; pick one and apply consistently | Not Started
Cross-Cutting | — | High | All 6 Regression Smoke Tests Not Tested | AUTH-004, PAT-001, ADM-001, LAB-003, DIS-003, SEC-001 all listed as NOT TESTED; must all PASS before post-fix regression | Not Started
Cross-Cutting | — | High | UAT Summary Sheet Blank | UAT Summary Pass/Fail/Blocked counts are all zero; must be completed using tester notes before Anna sign-off | Not Started
Cross-Cutting | — | High | Defect Log Blank | Defect Log not filled in; all FAIL items must be formally logged with TC reference, priority, description, and assigned developer | Not Started
Cross-Cutting | — | Medium | Encoder Audit Trail Missing | Forms do not record or display who encoded the data (user + timestamp); required for accountability and RA 10173 audit compliance | Not Started
Cross-Cutting | — | Medium | Responsive Layout Breaks on Tablet | Layout tested on iPad A16 shows responsiveness issues; must be fixed for non-desktop screen sizes before turnover | Not Started
Cross-Cutting | — | Medium | FHIR Identifier Fields Editable System-Wide | FHIR Identifier fields (Condition, Allergy, Immunization) are user-editable across modules; must be system-generated and read-only per PH Core FHIR R4 | Not Started

## Summary
WAH4H — Fix Progress Summary
Module | Total | Resolved | In Progress | Not Started | Blocked | % Done
Authentication | 13 | 0 | 0 | 13 | 0 | 0%
Patients | 31 | 0 | 0 | 31 | 0 | 0%
Admission | 10 | 0 | 0 | 10 | 0 | 0%
Appointments | 8 | 0 | 0 | 8 | 0 | 0%
Monitoring | 10 | 0 | 0 | 10 | 0 | 0%
Laboratory | 9 | 0 | 0 | 9 | 0 | 0%
Pharmacy | 7 | 0 | 0 | 7 | 0 | 0%
Discharge | 10 | 0 | 0 | 10 | 0 | 0%
Billing | 11 | 0 | 0 | 11 | 0 | 0%
eClaims | 5 | 0 | 0 | 5 | 0 | 0%
Dashboard | 2 | 0 | 0 | 2 | 0 | 0%
Admin Panel | 14 | 0 | 0 | 14 | 0 | 0%
Account Settings | 4 | 0 | 0 | 4 | 0 | 0%
Security | 5 | 0 | 0 | 5 | 0 | 0%
Cross-Cutting | 14 | 0 | 0 | 14 | 0 | 0%
TOTAL | 153 | 0 | 0 | 153 | 0 | 0%
Status Legend
Resolved
In Progress
Not Started
Blocked
Skipped

## Changelog
WAH4H — Fix Changelog
Date | Module | TC ID | Changed By | Status | Comments / Notes